## wc 09.02.26
Street Address | Town | Start Date | End Date | Start time | End time | TM Type | Promoter | Works | Works location description | Works location | Comment | Community Board
AMERSHAM ROAD | HIGH WYCOMBE | 2026-02-10 | 2026-02-11 | 0:00 | 23:59 | Two-way signals | Buckinghamshire Council | Lift and reset gully and renew materials around ironwork as per the method of measurement. Bedding frame with Envirobed mortar and surrounding the frame with PY4/5 resin mortar leaving 40mm depth for HRA2 way lightsGas pipeline nearbyRLee ¦1738376 (DR - Damaged Gully) | by utility pole and the beech tree pub | Carriageway |  | Wycombe
AMERSHAM ROAD | HIGH WYCOMBE | 2026-02-14 | 2026-02-23 | 8:00 | 17:00 | Multi-way signals | THAMES WATER | Excavate in C/W to exchange meter, washout, hydrant and valve and bypass back fll and reinstate | Junction of Terry Road HP13 6QB | Carriageway |  | Wycombe
CHAPEL LANE | HIGH WYCOMBE | 2026-02-11 | 2026-02-12 |  |  | Two-way signals | THAMES WATER | Remedial of defect works | O/S 119,CHAPEL LANE, HP12 4BY, HIGH WYCOMBE, SANDS | Carriageway |  | Wycombe
CORONATION ROAD | HIGH WYCOMBE | 2026-02-13 | 2026-02-14 |  |  | Multi-way signals | THAMES WATER | BOUNDARY BOX EXCHANGE IN FWAY | OPP STUART HOUSE, CORONATION ROAD, HIGH WYCOMBE, HP12 3RS | Footway |  | Wycombe
DESBOROUGH AVENUE | HIGH WYCOMBE | 2026-02-09 | 2026-02-09 | 9:30 | 15:30 | Multi-way signals | Buckinghamshire Council | DNO SERVICE IS POT ENDED IN GROUND, INSTALL NEW 3m BLACK LARGE BASE POST, FIT NEW SIMMONSIGNS MODUBEL LED BEACON, FIT 3 X REFLECTIVE BANDS, L3 ISOLATOR, NUMBER UNIT. PLUMB AND CONCRETE REQUIRED | Desborough Avenue High Wycombe outside Halfords BB37 and BB38 Belisha beacons | Verge |  | Wycombe
HATTERS LANE | HIGH WYCOMBE | 2026-02-10 | 2026-02-10 |  |  | Two-way signals | BT | TM Required box in a road. In connection with BC991GEC-HW-1375174-1-01 | From outside no.250 to outside no.254 | Carriageway |  | Wycombe
LONDON ROAD | HIGH WYCOMBE | 2026-02-10 | 2026-02-10 |  |  | Two-way signals | BT | CLEAR BLOCKAGE | Across C/W O/S 175 | Carriageway |  | Wycombe
LONDON ROAD | HIGH WYCOMBE | 2026-02-14 | 2026-02-22 | 8:00 | 17:00 | Multi-way signals | THAMES WATER | Excavate in F/W to install new Air valve backfill and reinstate | Opp junction of Gomm Road HP11 1HE | Footway |  | Wycombe
MICKLEFIELD ROAD | HIGH WYCOMBE | 2026-02-09 | 2026-02-11 |  |  | Two-way signals | THAMES WATER | VALVE REPACK IN FWAY | 48 MICKLEFIELD ROAD, HIGH WYCOMBE, HP13 7EN | Footway |  | Wycombe
OGILVIE ROAD | HIGH WYCOMBE | 2026-02-11 | 2026-02-11 |  |  | Multi-way signals | BT | CLEAR CW BLOCKAGE | Junction of Lidsay Avenue | Carriageway |  | Wycombe
RUTLAND STREET | HIGH WYCOMBE | 2026-01-05 | 2026-02-13 |  |  | Road closure | CADENT GAS LIMITED | GAS MAINS REPLACEMENT â€“ INSERT/ABANDON 42MTRS MAIN AND INSERT PE RELAY OR TRANSFER SERVICES FOR WORKS CARRIED OUT BY CADENT GAS | JNC WENDOVER STREET TO OPP OUTSIDE NO 1 WENDOVER STREET | Footway, Carriageway |  | Wycombe
SUFFIELD ROAD | HIGH WYCOMBE | 2026-02-03 | 2026-02-09 | 9:25 |  | Road closure | SCOTTISH AND SOUTHERN POWER DISTRIBUTION (SSEPD) | Fault locating works to Streetlight/Street Furniture, activities include excavation, restoration of supply, backfill and reinstatement | O/S 33 | Footway |  | Wycombe
TOTTERIDGE LANE | HIGH WYCOMBE | 2026-02-10 | 2026-02-10 |  |  | Two-way signals | BT | TM Required box in a road | From opposite the side of no.1 Richard Gardens to outside no.26 | Footway, Carriageway |  | Wycombe
WENDOVER STREET | HIGH WYCOMBE | 2026-01-05 | 2026-02-13 |  |  | Multi-way signals | CADENT GAS LIMITED | GAS MAINS REPLACEMENT â€“ INSERT/ABANDON 280MTRS MAIN AND INSERT PE RELAY OR TRANSFER SERVICES FOR WORKS CARRIED OUT BY CADENT GAS | JNC WEST END STREET TO JNC RUTLAND STREET | Footway, Carriageway | If they break into the S58 then the area we would need to do is circa 15m x 7m this would require a road closure. They must use boards / plates for the spoil as any scarring on the new S58 will require full width reinstatement | Wycombe
WEST WYCOMBE ROAD | HIGH WYCOMBE | 2026-02-09 | 2026-02-13 |  |  | Two-way signals | CADENT GAS LIMITED | LAY NEW DOMESTIC SERVICE 2M FROM MAIN IN CARRIAGEWAY | FOOTWAY OUTSIDE OF FORMER WHITE HORSE PUBLIC HOUSE | Footway |  | Wycombe
WYCHWOOD GARDENS | HIGH WYCOMBE | 2026-02-06 | 2026-02-13 | 8:00 | 17:00 | Road closure | Buckinghamshire Council | SAFETY BARRIER REPAIRS | WHOLE LENGTH | Footway, Verge |  | Wycombe
Note: Dates correct at time of publishing but could be subject to change. Excludes immediate works.
ADVANCE NOTICE: UK Highways M40 Ltd manages and maintains the M40 on behalf of National Highways. As part of their ongoing monitoring of the M40, it has come to their attention that necessary repair works will be required to the 50- year-old viaduct at Loudwater High Wycombe. In summary, works are expected to include concrete repairs, maintenance painting of steelwork, bearing refurbishment and replacement. The Loudwater Viaduct works are currently being planned to be undertaken from Spring 2026 to Winter 2026, and will require the closure of the junction 3 slip road, specific dates will be confirmed nearer the time. Diversion routes etc are not yet available as the works are still out to tender.